## Problem 5
[8 empty] | Total |  | Total
[8 empty] | Committed |  | Estimated
[7 empty] | Non- | and Non- |  | Cost | Variance
|  |  |  | Total |  | Committed | Committed | Committed | Cost | at | Over /
|  | Original | Change | Estimate | Committed | Costs | Costs | Costs | To | Completion | (Under)
Code | Description | Estimate | Orders | (C + D) | Costs | Invoiced | Invoiced | (F + H) | Complete | (I + J) | (K - E)
2400 | Sanitary Sewer | 25000 | 3200 | 28200 | 0 | 0 | 27365 | 27365 | 0 | 27365 | -835
2450 | Water Line | 31000 | 0 | 31000 | 0 | 0 | 31300 | 31300 | 450 | 31750 | 750
2500 | Storm Drain | 17000 | 0 | 17000 | 0 | 0 | 7236 | 7236 | 9764 | 17000 | 0
2900 | Outside Lighting | 23600 | 0 | 23600 | 23600 | 11230 | 0 | 23600 | 0 | 23600 | 0
|  | 96600 | 3200 | 99800 | 23600 | 11230 | 65901 | 89501 | 10214 | 99715 | -85