## Sheet4
CHAPTER 3: Example 4, 5 and 6
Project Management |  |  | Precedences; 1 time estimate
Data |  | Immediate Predecessors (1 per column)
Activity | Time | Pred 1 | Pred 2
A | 2
B | 3
C | 2 | A
D | 4 | A | B
E | 4 | C
F | 3 | C
G | 5 | D | E
H | 2 | F | G
Results
Activity | Early Start | Early Finish | Late Start | Late Finish | Slack
A | 0 | 2 | 0 | 2 | 0
B | 0 | 3 | 1 | 4 | 1
C | 2 | 4 | 2 | 4 | 0
D | 3 | 7 | 4 | 8 | 1
E | 4 | 8 | 4 | 8 | 0
F | 4 | 7 | 10 | 13 | 6
G | 8 | 13 | 8 | 13 | 0
H | 13 | 15 | 13 | 15 | 0
| Project | 15
Early start computations
A |  | 0 | 0
B |  | 0 | 0
C |  | 2 | 0
D |  | 2 | 3
E |  | 4 | 0
F |  | 4 | 0
G |  | 7 | 8
H |  | 7 | 13
Late finish computations
| A | B | C | D | E | F | G | H
A | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
B | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
C | 2 | 15 | 15 | 15 | 15 | 15 | 15 | 15
D | 4 | 4 | 15 | 15 | 15 | 15 | 15 | 15
E | 15 | 15 | 4 | 15 | 15 | 15 | 15 | 15
F | 15 | 15 | 10 | 15 | 15 | 15 | 15 | 15
G | 15 | 15 | 15 | 8 | 8 | 15 | 15 | 15
H | 15 | 15 | 15 | 15 | 15 | 13 | 13 | 15
| 2 | 4 | 4 | 8 | 8 | 13 | 13 | 15
Graph |  | Critical Activity | Noncritical Activity | Slack | 9 | Graph |  | Critical Activity | Noncritical Activity | Slack
A | 0 | 2 | 0 | 0 | 8 | H | 13 | 2 | 0 | 0
B | 0 | 0 | 3 | 1 | 7 | G | 8 | 5 | 0 | 0
C | 2 | 2 | 0 | 0 | 6 | F | 4 | 0 | 3 | 6
D | 3 | 0 | 4 | 1 | 5 | E | 4 | 4 | 0 | 0
E | 4 | 4 | 0 | 0 | 4 | D | 3 | 0 | 4 | 1
F | 4 | 0 | 3 | 6 | 3 | C | 2 | 2 | 0 | 0
G | 8 | 5 | 0 | 0 | 2 | B | 0 | 0 | 3 | 1
H | 13 | 2 | 0 | 0 | 1 | A | 0 | 2 | 0 | 0
Enter the times in the appropriate column(s). Enter the precedences, one per column. (Do not try to use commas).